## Slide 1: Predictive modeling of Material Take-off Overrun Risks in Brownfield EPC Projects
A Dual-Task Machine Learning Approach to Quantifying MTO Growth for Proactive Cost Control
Engr. Julie Anne-Mae V. Villanueva
Postgraduate Diploma in Artificial Intelligence and Machine Learning
Asian Institute of Management (AIM)

## Slide 2: The Brownfield Engineering Challenge
The Reality of Revamps
The Constraint Triangle
The Business Impact
Modifying active, aging plants presents massive logistical hurdles compared to greenfield projects.
Incomplete legacy blueprints
Tight physical and spatial constraints
High tie-in density to operating headers
Initial Material Take-Off (MTO) estimates drawn from early Front-End Engineering Design (FEED) rarely match physical reality, leading to severe volume growth as designs mature.

## Slide 3: The Flaw in Flat Contingencies
Project controls teams typically apply a static, across-the-board 10% to 15% material buffer to hedge against volume growth.
This treats benign, straight-run utility pipes identically to high-pressure, severe-temperature, or toxic exotic alloy circuits.
The Consequences of Getting it Wrong:
Over-estimating: Traps millions in idle working capital, bloating EPC bid prices and making proposals uncompetitive.
Under-estimating: Causes catastrophic field shortages, triggering high-premium air freight and expensive craft standby delays.

## Slide 4: Project Objectives: Transforming Data into Risk Intelligence
Replacing subjective markups with an empirical, data-driven machine learning pipeline.
Flag High-Risk Overruns (Early Warning): Identify specific process subsystems that have a high probability of exceeding a 15% material growth before the design is frozen.
Quantify Exact Material Growth (Smart Shopping List): Predict the exact percentage volume overrun based on process severity and spatial constraints.
Optimize Contingency Allocation: Empower project managers to justify dynamic, risk-adjusted material allowances to protect both the schedule and the bottom line.

## Slide 5: A Dual-Task Machine Learning Framework
Trained on 8,500 domain-synthesized brownfield subsystems mimicking real-world constraints.
Task 1: Classification (Risk Flagging)
Task 2: Regression (Growth Quantification)
Model: Champion LightGBM Classifier
Result: Achieves a 97.41% PR-AUC score.
Value: Highly sensitive to predicting "danger zones" without triggering excessive false alarms.
Model: Champion LightGBM Regressor
Result: Restricts residual variance to ~3.5% (RMSE).
Value: Provides a mathematically proven uncertainty band, drastically outperforming standard linear estimating techniques.

## Slide 6: Business KPI 1: Proactive Cost & Schedule Control
Sharper Bid Competitiveness
Unnecessary contingency padding on low-complexity utility circuits (e.g., carbon steel, 100% laser-scanned) is pruned, allowing linear, more competitive LSTK bids.
Targeted Protection for Critical Paths
Capital is disproportionately redirected to high-severity, exotic alloy lines (Duplex, Inconel).
Schedule Protection
Prevents field shortages that trigger vendor expedited shop rates and craft standby delays.

## Slide 7: Business KPI 2: Optimizing Working Capital
Capital Allocation on a $20M Bulk Piping Package
Conventional 15% Blanket Contingency:
$3M allocated as a static hedge.
ML-Adjusted Allowance (±3.5% Uncertainty Band):
$0.7M to $1.4M allocated dynamically per line item.
Net Working Capital Released:
Frees up $1.6M to $2.3M in trapped working capital per $20M package.

## Slide 8: The “Glass Box” Approach for Engineers
Model logic is fully transparent to technical audit boards using Local SHAP Explanations.
The model relies on physical engineering laws, not black-box chance.
Top Drivers of Overruns:
  High Brownfield Complexity Penalty (dense tie-ins)
  Lack of 3D Laser Scan Coverage
  Low FEED Gate Maturity (30% vs. 90%)
The Verdict: The model mathematically confirms that spatial uncertainty and the early design stage are the largest contributors to bulk material growth.

## Slide 9: Local Explainability (Line PL-00005 Audit)
Historical Baseline Material Growth: 19.37%
Risk Escalators Identified by ML:
30% FEED maturity (+5.16% penalty)
Toxic fluid service (+3.23% penalty)
Extreme design pressure of 240.9 barg (+1.86% penalty)
Risk Mitigators Identified by ML:
97.3% 3D laser scan coverage (-1.67% credit)
Final ML Verdict: Targeted 27.73% buffer, precisely matching the actual historical closeout need of 27.54%. A traditional 15% blanket markup would have left this critical line severely under-budgeted.
Tracing every dollar of contingency back to a physical constraint.

## Slide 10: Algorithmic Fairness & Unbiased Estimation
Evaluates engineering physics (pressures, tie-ins), not human or commercial metadata.
Validated using Equalized Error Distribution (Group Residual Parity) across subgroups.
Zero-centered error distributions guarantee statistical parity.
The algorithm does not penalize outsourced contractors or regional suppliers, ensuring completely equitable bid allocations.

## Slide 11: Thank you
Special thanks to the AIM faculty, program leader, and my cohort for their guidance throughout this program journey.
Julie Anne-Mae V. Villanueva
jamvanta06@gmail.com